## Sheet1
Estimated Hours: | 25 | See below for calculation of estimation
Individual Hours: | 5
Actual Hours:
|  | Date: | Regan | Date: | Andrew | Date: | Jui | Date: | Chen | Date: | Natasha
|  | 2021-09-21 | 0.5 | 2021-09-21 | 0.5 | 2021-09-21 | 0.5 | 2021-09-21 | 0.5 | 2021-09-21 | 0.5
|  | 2021-09-26 | 0.5 | 2021-09-30 | 4 | 2021-09-30 | 4 | 2021-09-29 | 1 | 2021-09-26 | 0.5
|  | 2021-09-30 | 4 | 2021-10-05 | 4 | 2021-10-05 | 4 | 2021-09-30 | 4 | 2021-09-30 | 4
|  | 2021-10-04 | 2 | 2021-10-06 | 1 | 2021-10-06 | 2 | 2021-10-05 | 5 | 2021-10-05 | 5
|  | 2021-10-05 | 4 | 2021-10-07 | 3 | 2021-10-07 | 3 | 2021-10-06 | 0.5 | 2021-10-07 | 5
|  | 2021-10-06 | 2 | 2021-10-08 | 1 | 2021-10-08 | 1 | 2021-10-07 | 5 | 2021-10-08 | 5
|  | 2021-10-08 | 2 | 2021-10-09 | 4 |  |  | 2021-10-08 | 1
[8 empty] | 2021-10-09 | 2
|  | Total: | 15 |  | 17.5 |  | 14.5 |  | 19 |  | 20
|  | Total Hours: | 86
Total Lines of code for project 1: | 958 | <-- includes all lines of codes including comments
Total Hours on project | 86
LOC/hr | 11.1395 | - not necessarily accurate for LOC/hr since the total hours also included the time spent on other aspects of the project, but for estimation will assume those hours will be the same time spent for this project
Estimate LOC for AI | 200 | based off LOC for our other class files from project 1
Estimate LOC for added feature | 150
Estimate total LOC project 2: | 350
350 LOC/ 15.206 LOC per hr = | 31.4196 | Based on Project 1 the estimate of hours will be about 25 hrs.